## Sheet2
Integration | Document | Schema | Testfile | Mapping | BY who | Comments
ESIS001_EDIPO_DD_TO_EDI | ESIS001_EDIPO_DD_TO_xCBL.xlsx | ESIS001_DD.mtt | QA.ESIS001_F_001.IN.rfh | ESIS001_EDIPO_DD_TO_xCBL.mms | Done, Mozhgan
ESIS001_EDIPO_DD_TO_EDI_SPLT | [5 empty] | It's going to be handled in DataPower
ESIS001_EDIPO_EBM_TO_EDI | ESIS001_EDIPO_EBM_TO_xCBL.xlsx |  |  |  | Mozhgan, Working on
ESIS001_EDIPO_EDI_TO_DD | ESIS001_EDIPO_xCBL_TO_DD.xlsx | ESIS001_DD.mtt | ESIS001_DD_Input.txt | ESIS001_EDIPO_xCBL_TO_DD.mms | Örjan Imran: mapping, Spec, Done 20140214
ESIS001_EDIPO_EDI_TO_EBM | ESIS001_EDIPO_xCBL_TO_EBM.xlsx | ESIS001_EDIPO_EDI_TO_EBM_Body.xsd ESIS001_EDIPO_EDI_TO_EBM_Envelope.xsd MBM_Envelope.xsd | Output: QA.ESIS001_EDIPO.QM_MEC_006.rfh |  | Mozhgan, In work | XSD was build against testfiles which didn't contain all fields, have tried to find an schema from MEC environment, now found a one, just need to validate it and then begin the mapping
ESIS001_EDIPO_EDI_TO_XML | ESIS001_EDIPO_xCBL_TO_XML.xlsx | ESIS001_EDIPO_xCBL_To_XML.xsd | Input: QL.ESIS001_EDIPO_EDI_TO_XML_023.IN Output: QA.ESIS001_EDIPO.QMATLS_025.rfh | ESIS001_EDIPO_xCBL_TO_XML.mms | Done, Mozhgan
ESIS001_EDIPO_EDIX_TO_EDI |  |  |  | Routing |  | The only real thing it does is that it cast the message from one CCSID to another and then routes the message and logs it
ESIS001_EDIPO_XML_TO_EDI | ESIS001_EDIPO_XML_TO_xCBL.xlsx | ESIS001_EDIPO_XML_TO_xCBL.xsd | Input: QL.RTQ_ESIS001_S_1.rfh | ESIS001_EDIPO_XML_TO_xCBL.mms | Done, Mozhgan
ESIS001_EDIPO_XML_TO_EDI_SPLIT | [5 empty] | This flow sends messages to both ESIS001_EDIPO_XML_TO_EDI (which is as expected) and ESIS005_EDIDN_XML_TO_EDI. Should it do that? According ESAB, this flow is not needed anymore.
ESIS002_EDIOC_DD_TO_EDI | ESIS001_EDIPO_xCBL_TO_DD.xlsx | ESIS002_DD.mtt | ESIS002.DD_Input.txt | ESIS002_EDIOC_DD_TO_xCBL.mms | Örjan Imran: Map Done 20170218
ESIS002_EDIOC_DD_TO_EDI_SPLT |  | ESIS002_DD.mtt | ESIS002.DD0A_MultipleMessages_Input.txt, ESIS002.DD0D0A_MultipleMessages_Input.txt |  | Örjan | It's going to be handled in DataPower
ESIS002_EDIOC_EBM_TO_EDI
ESIS002_EDIOC_EDI_TO_DD | ESIS002_EDIOC_xCBL_TO_DD.xlsx | ESIS002_DD.mtt | ESIS002.DD_Input.txt | ESIS002_EDIOC_xCBL_TO_DD.mms | Örjan Mozhgan: Map, Spec Done 20140218
ESIS002_EDIOC_EDI_TO_EBM
ESIS002_EDIOC_EDI_TO_XML | ESIS002_EDIOC_xCBL_TO_XML.xlsx | ESIS002_EDIOC_xCBL_TO_XML.xsd | Output: QA.ESIS002_EDIOC.QMATLS_018.rfh Input: QL.ESIS002_EDIOC_EDI_TO_XML_006.IN | ESIS002_EDIOC_xCBL_TO_XML.mms | Done, Mozhgan | PurchaseOrder Confirmation
ESIS002_EDIOC_EDI_TO_EDIX | ESIS002_EDIOC_xCBL_TO_EDIX.xlsx | esab_env.mtt edifd96a.mtt | OrderResponseSample-ABC_xCBL40.xml | ESIS002_EDIOC_xCBL_TO_EDIX.mms | Mozhgan, Done 20140213 | This mapping consists av 2 stages; 1. Maps from Edifact to DD to be able to split the files (one order per message) 2. Maps from DD back to Edifact to send out the message. According Richard on 20140211: Now we have a new intermediate format [xCBL] Hence the requirement to map to EDIFACT.
ESIS002_EDIOC_XML_TO_EDI | ESIS002_EDIOC_XML_TO_xCBL.xlsx | ESIS002_EDIOC_XML_TO_xCBL.xsd | QL.ESIS002_EDIOC_XML_TO_EDI_751067.IN.rfh | ESIS002_EDIOC_XML_TO_xCBL.mms | Done, Mozhgan | CustomerOrderConfirmation
ESIS002_EDIOC_XML_TO_EDI_SPLIT | [5 empty] | It's going to be handled in DataPower
ESIS003_EDIDA_DD_TO_EDI | ESIS003_EDIDA_DD_TO_xCBL.xlsx | ESIS003_DD.mtt esab_env_MM.mtt | ESIS003_A_IN_01.txt | ESIS003_EDIDA_DD_TO_xCBL.mms | Örjan Mozhgan, Done 140228
ESIS003_EDIDA_DD_TO_EDI_SPLT |  | ESIS003_DD0A_IN.mtt | ESIS003_DD0A_Input.txt, ESIS003_DD0D0A_Input.txt, ESIS003_DD0D0A_MultipleMessages_Input.txt |  | Örjan | It's going to be handled in DataPower
ESIS003_EDIDA_EDI_TO_DD |  | ESIS003_DD.mtt, ESIS003_DD0A_OUT.mtt | ESIS003_DD_Input.txt |  | Örjan | Mapping maps from DD to DD0A (flat file with <LF> line breaks). Only used for specific contracts.
ESIS003_EDIDA_DD_TO_EDI
ESIS003_EDIDA_DD_TO_EDI_SPLT
ESIS003_EDIDA_EBM_TO_EDI
ESIS003_EDIDA_EDI_TO_DD
ESIS003_EDIDA_EDI_TO_EBM
ESIS003_EDIDA_EDI_TO_EDIX
ESIS003_EDIDA_XML_TO_EDI
ESIS003_EDIDA_EDI_TO_XML
ESIS004_EDIIN_DD_TO_EDI |  | ESIS004_DD.mtt | ESIS004_DD_Input_corrected_sample.txt |  | Örjan | Typetree is validated
ESIS004_EDIIN_DD_TO_EDI_SPLT
ESIS004_EDIIN_EDI_TO_DD
ESIS005_EDIDN_DD_ROUTE |  | ESIS005_DD.mtt | ESIS005_DD_Input.txt |  | Örjan | TypeTree is validated.
ESIS005_EDIDN_DD_ROUTE_SPLT
ESIS005_EDIDN_EDI_TO_DD