## Sheet1
Integration | Document | Schema | Testfile | Mapping | BY who | Comments 20140211
.
ESIS001_EDIPO_DD_TO_EDI | ESIS001_EDIPO_DD_TO_EDI.xlsx | ESIS001_DD.mtt | QA.ESIS001_F_001.IN.rfh | ESIS001_EDIPO_DD_TO_EDI.mms | Done, Mozhgan
ESIS001_EDIPO_DD_TO_EDI_SPLT | [5 empty] | SPLIT is not applicable
ESIS001_EDIPO_EBM_TO_EDI
ESIS001_EDIPO_EDI_TO_DD |  | ESIS001_DD.mtt | ESIS001_DD_Input.txt |  | Örjan
ESIS001_EDIPO_EDI_TO_EBM | ESIS001_EDIPO_EDI_TO_EBM.xlsx | ESIS001_EDIPO_EDI_TO_EBM_Body.xsd ESIS001_EDIPO_EDI_TO_EBM_Envelope.xsd MBM_Envelope.xsd | Output: QA.ESIS001_EDIPO.QM_MEC_006.rfh |  | Mozhgan, In work | XSD was build against testfiles which didn't contain all fields, have tried to find an schema from MEC environment, now found a one, just need to validate it and then begin the mapping
ESIS001_EDIPO_EDI_TO_XML | ESIS001_EDIPO_EDI_TO_XML.xlsx | ESIS001_EDIPO_EDI_To_XML.xsd | Input: QL.ESIS001_EDIPO_EDI_TO_XML_023.IN Output: QA.ESIS001_EDIPO.QMATLS_025.rfh | ESIS001_EDIPO_EDI_TO_XML.mms | Done, Mozhgan
ESIS001_EDIPO_EDIX_TO_EDI | [5 empty] | The only real thing it does is that it cast the message from one CCSID to another and then routes the message and logs it How it would work with xCBL? Routing or transformating?
ESIS001_EDIPO_XML_TO_EDI | ESIS001_EDIPO_XML_TO_EDI.xlsx | ESIS001_EDIPO_XML_TO_EDI.xsd | Input: QL.RTQ_ESIS001_S_1.rfh | ESIS001_EDIPO_XML_TO_EDI.mms | Done, Mozhgan
ESIS001_EDIPO_XML_TO_EDI_SPLIT | [5 empty] | This flow sends messages to both ESIS001_EDIPO_XML_TO_EDI (which is as expected) and ESIS005_EDIDN_XML_TO_EDI. Should it do that? According ESAB, this flow is not needed anymore, Correct?
l
ESIS002_EDIOC_DD_TO_EDI |  | ESIS002_DD.mtt | ESIS002.DD_Input.txt |  | Örjan
ESIS002_EDIOC_DD_TO_EDI_SPLT |  | ESIS002_DD.mtt | ESIS002.DD0A_MultipleMessages_Input.txt, ESIS002.DD0D0A_MultipleMessages_Input.txt |  | Örjan | SPLIT is not applicable
ESIS002_EDIOC_EBM_TO_EDI
ESIS002_EDIOC_EDI_TO_DD |  | ESIS002_DD.mtt, ESIS002_DD0A_OUT.mtt | ESIS002.DD_Input.txt |  | Örjan
ESIS002_EDIOC_EDI_TO_EBM
ESIS002_EDIOC_EDI_TO_XML | ESIS002_EDIOC_EDI_TO_XML.xlsx | ESIS002_EDIOC_EDI_TO_XML.xsd | Output: QA.ESIS002_EDIOC.QMATLS_018.rfh Input: QL.ESIS002_EDIOC_EDI_TO_XML_006.IN | ESIS002_EDIOC_EDI_TO_XML.mms | Done, Mozhgan | PurchaseOrder Confirmation
ESIS002_EDIOC_EDI_TO_EDIX | ESIS002_EDIOC_EDI_TO_EDIX.xlsx |  |  |  | Mozhgan, In work | This mapping consists av 2 stages; 1. Maps from Edifact to DD to be able to split the files (one order per message) 2. Maps from DD back to Edifact to send out the message. According Richard on 20140211: Now we have a new intermediate format [xCBL] Hence the requirement to map to EDIFACT.
ESIS002_EDIOC_XML_TO_EDI | ESIS002_EDIOC_XML_TO_EDI.xlsx | ESIS002_EDIOC_XML_TO_EDI.xsd | QL.ESIS002_EDIOC_XML_TO_EDI_751067.IN.rfh | ESIS002_EDIOC_XML_TO_EDI.mms | Done, Mozhgan | CustomerOrderConfirmation
ESIS002_EDIOC_XML_TO_EDI_SPLIT | [5 empty] | SPLIT is not applicable
ESIS003_EDIDA_DD_TO_EDI |  | ESIS003_DD.mtt | ESIS003_DD_Input.txt |  | Örjan
ESIS003_EDIDA_DD_TO_EDI_SPLT |  | ESIS003_DD0A_IN.mtt | ESIS003_DD0A_Input.txt, ESIS003_DD0D0A_Input.txt, ESIS003_DD0D0A_MultipleMessages_Input.txt |  | Örjan | SPLIT is not applicable
ESIS003_EDIDA_EDI_TO_DD |  | ESIS003_DD.mtt, ESIS003_DD0A_OUT.mtt | ESIS003_DD_Input.txt |  | Örjan | Mapping maps from DD to DD0A (flat file with <LF> line breaks). Only used for specific contracts.
ESIS004_EDIIN_DD_TO_EDI |  | ESIS004_DD.mtt | ESIS004_DD_Input_corrected_sample.txt |  | Örjan | Typetree is validated
ESIS004_EDIIN_DD_TO_EDI_SPLT
ESIS004_EDIIN_EDI_TO_DD
ESIS005_EDIDN_DD_ROUTE |  | ESIS005_DD.mtt | ESIS005_DD_Input.txt |  | Örjan | TypeTree is validated.
ESIS005_EDIDN_DD_ROUTE_SPLT
ESIS005_EDIDN_EDI_TO_DD